## Tentative work schedule
Tentative Work schedule

Banking Application

Item No.	Description	Start Date	Finish Date	04/21/22	04/22/22			04/25/22	04/26/22	04/27/22	04/28/22	04/29/22			05/02/22	05/03/22	05/04/22	05/05/22	05/06/22			05/09/22	05/10/22	05/11/22	05/12/22	05/13/22			05/16/22	05/17/22	05/18/22
1	Document Preparation	04/21/22	04/22/22
2	Planning Phase	04/25/22	04/26/22
3	Requirement Analysis Phase	04/26/22	04/27/22
4	Designing Phase	04/27/22	04/29/22
5	Database preparation Phase	04/29/22	04/30/22
6	Pushing all updated document to git-hub	05/01/22	05/02/22
7	Zero Development Phase	05/02/22	05/05/22
8	Checkpoint (Thursday May 5th 2022)	05/05/22	05/05/22
9	First Development Phase	05/05/22	05/09/22
10	Testing phase	05/10/22	05/10/22
11	Bug Fixing Phase	05/11/22	05/11/22
12	Pushing all updated document to git-hub	05/12/22	05/12/22
13	Second Development Phase	05/13/22	05/14/22
14	Testing phase	05/16/22	05/16/22
15	Bug Fixing Phase	05/16/22	05/16/22
16	Pushing all updated document to git-hub	05/17/22	05/17/22
16	Final Submission	05/17/22	05/17/22
17	Presentation Day	05/18/22	05/18/22

## Login and Home Page
username

password

Login		Sign Up

					Welcome to Bank_P0 Home Page

					Account Info.		Transfer		Withdraw		Deposit		Help		Logout

					Saving Account History

					Date		Transaction Message		Available Balance		Remark

					Checking Account History

					Date		Transaction Message		Available Balance		Remark

## User Registration page
			Welcome to Registration page					Welcome to Deposit page

				Amount to Deposit
First Name					SSN
				Previous balance
Last Name					Address 1
				New Balance
DOB (mm/dd/yyyy)					Address 2

Gender					City					Submit		Logout

Username					Zip code				State

			Terms and Condition

				Welcome to Withdrawal page

				Amount to Withdraw

				Previous balance

				New Balance

				Submit		Logout